## Tabelle1
Task | Task Description | Duration
1 | Kickoff | 1
2 | 1st Submission | 11
3 | Requirements analysis | 7
4 | Process Model | 3
5 | Verification of git repository | 1
6 | 1st Iteration | 21
7 | Terminal based game | 13
8 | Multiplayer functionality | 5
9 | Prevention of invalid moves | 2
10 | JUnit Tests | 3
11 | Documentation | 2
12 | Testing | 3
13 | 1st Milestone | 0
14 | 2nd Iteration | 28
15 | Design a 2D GUI | 20
16 | Implementation of basic AI | 20
17 | JUnit Tests | 4
18 | Documentation | 2
19 | Testing | 2
20 | 2nd Milestone | 0
21
22 | 3rd Iteration | 27
23 | Save/load functionality | 6
24 | Chess Clock Implementation | 6
25 | Bilingual interface implementation | 6
26 | Resize window functionality | 6
27 | Chess puzzle implementation | 7
28 | JUnit Tests | 10
29 | Documentation | 2
30 | Testing | 3
31 | 3rd Milestone | 0