## Tabelle1
Task | Task Description | Duration
1 | Kickoff | 1
2 | 1st Iteration | 32
3 | Analysis | 10
4 | Requirements analysis | 7
5 | Process Planing | 3
6 | Planing & Design | 4
7 | Create Backlog items | 2
8 | Create user stories | 1
9 | Documentation | 1
10 | Implementation | 13
11 | Terminal based game | 9
12 | Multiplayer functionality | 3
13 | Prevention of invalid moves | 1
14 | Testing | 5
15 | JUnit Tests | 3
16 | White Box testing | 2
17 | 1st Milestone | 0
18 | 2nd Iteration | 28
19 | Planing & Design | 4
20 | Update Backlog items | 1
21 | Create user stories | 2
22 | Documentation | 1
23 | Implementation | 19
24 | Design a 2D GUI | 7
25 | Implementation of basic AI | 12
26 | Testing | 5
27 | JUnit Tests | 3
28 | White Box testing | 2
29 | 2nd Milestone | 0
30 | 3rd Iteration | 28
31 | Planing & Design | 4
32 | Update Backlog items | 1
33 | Create user stories | 2
34 | Documentation | 1
35 | Implementation | 19
36 | Save/load functionality | 6
37 | Chess Clock Implementation | 6
38 | Bilingual interface implementation | 3
39 | Resize window functionality | 2
40 | Chess puzzle implementation | 2
41 | Testing | 5
42 | JUnit Tests | 3
43 | White Box testing | 2
44 | 3rd Milestone | 0